PeopleSoft to Cloud ERP

A Migration Framework for Mid-Size Enterprises

_______________________________________________

Payal Devendra Jarviya

MBA Candidate | SKKU Graduate School of Business, Seoul

Former IT Analyst | NTT DATA North America | PeopleSoft Oracle Practice

2025

Executive Summary

Many mid-size enterprises across industries continue to rely on legacy PeopleSoft ERP systems that were implemented a decade or more ago. While these systems remain functional, they increasingly struggle to meet the demands of modern business operations, including real-time analytics, remote accessibility, scalability, and integration with emerging technologies such as AI and machine learning.

This framework provides a structured, practical approach to migrating from on-premises PeopleSoft environments to modern cloud ERP platforms. It is designed specifically for mid-size enterprises that operate with limited IT budgets, lean transformation teams, and complex stakeholder environments.

Drawing on four years of hands-on PeopleSoft implementation and enterprise systems consulting experience at NTT DATA North America, this framework addresses the full migration lifecycle: from readiness assessment and business case development through to go-live and post-migration optimization.

Key Takeaways Migration from PeopleSoft to cloud ERP is not just a technical upgrade. It is a business transformation. The biggest migration failures stem from poor change management and stakeholder alignment, not technical issues. A phased migration approach significantly reduces risk compared to a full cutover. Mid-size enterprises must prioritize data integrity and user adoption above all else during migration. Cloud ERP delivers long-term ROI through reduced infrastructure costs, real-time reporting, and AI-ready architecture.

1.  The Case for Migration

1.1 Why PeopleSoft Enterprises Are at a Crossroads

PeopleSoft, now owned by Oracle, remains one of the most widely deployed ERP platforms globally, particularly in HR, finance, and supply chain functions. However, organizations that implemented PeopleSoft in the early 2000s or 2010s now face a convergence of pressures that make staying on the platform increasingly costly and strategically risky.

| Vendor Direction | Oracle has shifted its primary development investment toward Oracle Cloud (Fusion). PeopleSoft receives maintenance updates but limited innovation. |
| --- | --- |
| Infrastructure Costs | On-premises PeopleSoft requires significant hardware, DBA support, and ongoing patching. Cloud ERP eliminates most of this overhead. |
| Integration Complexity | Modern enterprises need seamless integration with CRM, BI, and AI tools. PeopleSoft integrations are often custom-built and brittle. |
| Talent Availability | The pool of skilled PeopleSoft consultants is shrinking. Cloud ERP skills are far more available in the current market. |
| Remote Access Limitations | PeopleSoft was designed for on-premises access. Post-pandemic work models demand cloud-native accessibility. |
| Reporting Capabilities | PeopleSoft reporting requires significant technical knowledge. Modern cloud ERPs offer self-service analytics and real-time dashboards. |

1.2 What Mid-Size Enterprises Stand to Gain

- Reduced total cost of ownership through elimination of on-premises infrastructure

- Faster deployment of new features and capabilities through vendor-managed updates

- Improved data visibility with built-in analytics and reporting dashboards

- Greater scalability to support business growth without additional infrastructure investment

- Enhanced security and compliance through cloud vendor certifications

- AI and machine learning capabilities that are natively integrated into modern cloud ERP platforms

2.  Pre-Migration Assessment

2.1 Organizational Readiness Checklist

Before initiating any migration, enterprises must conduct an honest assessment of their current state. Rushing into migration without this foundation is one of the leading causes of failed ERP transformations.

| Business Process Clarity | Are your current PeopleSoft business processes documented? Migration is an opportunity to clean up and standardize processes, not just replicate them in a new system. |
| --- | --- |
| Data Quality | How clean is your existing data? Migrating bad data to a new system does not fix data problems. It amplifies them. |
| Stakeholder Alignment | Do key business leaders understand and support the migration? Without executive sponsorship, ERP migrations stall. |
| IT Capability | Does your internal IT team have cloud skills? Identify gaps early and plan for upskilling or external support. |
| Budget Clarity | Have you accounted for the full cost of migration including licenses, implementation, training, and contingency? |
| Change Management Plan | Who will manage user adoption? Technology is only 30% of ERP success. People and process are the remaining 70%. |

2.2 Common Pitfalls Observed in PeopleSoft Environments

Based on enterprise consulting experience, the following issues are consistently found in mid-size PeopleSoft environments prior to migration:

- Highly customized PeopleSoft configurations that have deviated significantly from vanilla functionality, making like-for-like mapping to cloud ERP difficult

- Undocumented workarounds and manual processes that have been built around system limitations over time

- Data inconsistencies between modules, particularly between HR, Finance, and Supply Chain

- Shadow systems such as Excel spreadsheets and Access databases that have grown up alongside PeopleSoft to fill functionality gaps

- Lack of a single data owner or data governance framework, resulting in duplicated or conflicting records

- Insufficient user documentation, meaning institutional knowledge exists only in the heads of long-tenured staff

3.  The Migration Framework

3.1 Framework Overview

This framework follows a five-phase approach designed to balance speed with risk management. Each phase has defined objectives, activities, and deliverables. The framework is modular, meaning organizations can adjust timelines and scope based on their specific context.

| Phase | Timeline | Key Activities | Deliverable |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1 to 4 | Current state assessment, stakeholder mapping, business case development | Migration Readiness Report |
| Phase 2 | Weeks 5 to 10 | Cloud ERP vendor evaluation, fit-gap analysis, data audit | Vendor Selection Report + Data Quality Assessment |
| Phase 3 | Weeks 11 to 20 | System configuration, data cleansing, integration design, UAT planning | Configured Cloud ERP Environment |
| Phase 4 | Weeks 21 to 26 | UAT execution, training delivery, cutover planning, parallel run | UAT Sign-off + Trained User Base |
| Phase 5 | Weeks 27 to 30 | Go-live, hyper care support, performance monitoring, lessons learned | Live System + Post-Migration Review |

3.2 Phase 1: Discovery and Business Case

Objectives

- Establish a clear understanding of the current PeopleSoft landscape

- Identify key business drivers and pain points motivating migration

- Build a compelling business case with quantified benefits and costs

- Secure executive sponsorship before committing resources

Key Activities

- Conduct stakeholder interviews across Finance, HR, Supply Chain, and IT to map current pain points

- Document all active PeopleSoft modules and customizations in use

- Identify integrations between PeopleSoft and other enterprise systems

- Quantify current infrastructure and maintenance costs

- Develop a high-level ROI model comparing stay-the-course versus migration scenarios

- Present business case to executive leadership and secure formal sign-off

Insight from Practice In enterprise consulting engagements, the business case phase is often underestimated. Organizations rush to vendor selection without first aligning on why they are migrating and what success looks like. A strong business case does three things: it quantifies the cost of inaction, it sets realistic expectations about migration complexity, and it establishes the metrics by which success will be measured post go-live.

3.3 Phase 2: Vendor Selection and Fit-Gap Analysis

Cloud ERP Evaluation Criteria

| Functional Coverage | Does the platform cover your core modules: HR, Finance, Procurement, Supply Chain? |
| --- | --- |
| Migration Support | Does the vendor offer PeopleSoft-specific migration tools, data templates, or accelerators? |
| Total Cost of Ownership | Compare license costs, implementation costs, and ongoing subscription fees over a 5-year horizon. |
| Integration Ecosystem | How easily does the platform integrate with your existing CRM, BI, and third-party tools? |
| Local Support | Does the vendor have implementation partners and support capability in your region? |
| AI and Analytics | What native AI and reporting capabilities are included in the base license? |

Fit-Gap Analysis Process

A fit-gap analysis compares your current PeopleSoft business processes against the standard functionality of the target cloud ERP. The output is a structured document that categorizes each process as:

- Fit: The cloud ERP handles this process in its standard configuration with no changes required

- Partial Fit: The cloud ERP can handle this process but requires minor configuration

- Gap: The cloud ERP does not support this process in standard configuration and requires customization or a workaround

The fit-gap output directly informs the implementation scope, timeline, and budget. A high number of gaps is a warning signal that either the vendor is not the right fit, or that the enterprise needs to redesign its processes before migrating.

3.4 Phase 3: Build and Configure

This is the most technically intensive phase of the migration. It involves configuring the cloud ERP to reflect agreed business processes, cleaning and preparing data for migration, and designing integrations with connected systems.

Data Migration Approach

- Identify all data entities to be migrated: master data, transactional data, historical data

- Conduct data profiling to identify quality issues, duplicates, and missing values

- Define data cleansing rules and assign data owners accountable for resolution

- Build and test data migration scripts using vendor-provided templates where available

- Establish a data validation framework to verify completeness and accuracy post-migration

- Agree on historical data cutover date: how many years of history will migrate versus archive

3.5 Phase 4: Testing and Training

UAT Framework

User Acceptance Testing is where business users validate that the configured system meets their requirements. It is not an IT testing exercise. Business users must own UAT.

| Test Scope | Cover all in-scope business processes end-to-end, not just individual transactions |
| --- | --- |
| Test Data | Use realistic, anonymized production data wherever possible |
| Defect Management | Classify defects as critical, major, or minor with clear resolution SLAs |
| Sign-off Criteria | Define what percentage of test cases must pass before go-live approval |
| Regression Testing | Re-test previously passing scenarios after each defect fix |

Training Strategy

- Role-based training: different user groups need different training content

- Deliver training as close to go-live as possible to maximize retention

- Create quick reference guides for common tasks in the new system

- Identify and train super users in each department who can support peers post go-live

- Record training sessions for onboarding future employees

3.6 Phase 5: Go-Live and Hypercare

Go-live is not the end of the migration. It is the beginning of the most critical support period. Hypercare refers to the intensive support provided in the first four to eight weeks after go-live, when users are adjusting to the new system and issues are most likely to surface.

Hypercare Best Practices Maintain a war room or dedicated support channel for the first two weeks post go-live. Track daily system performance metrics and user-reported issues. Assign dedicated functional consultants on standby to resolve critical issues within hours. Conduct weekly lessons learned sessions during hyper care to identify recurring patterns. Do not decommission PeopleSoft immediately. Run parallel for at least four weeks as a safety net.

4.  Risk Management

4.1 Key Migration Risks and Mitigations

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Data loss or corruption during migration | High | Critical | Implement multiple data validation checkpoints and maintain PeopleSoft as backup during parallel run |
| User resistance and low adoption | High | High | Invest in change management from Phase 1. Involve business users in design decisions, not just testing |
| Scope creep extending timeline and budget | Medium | High | Define clear scope boundaries in Phase 1. Use a formal change request process for any additions |
| Integration failures with connected systems | Medium | High | Map all integrations in Phase 1. Test integrations in a dedicated environment before UAT |
| Key person dependency | Medium | Medium | Document all decisions and configurations. Crosstrain team members throughout the project |
| Vendor support limitations | Low | Medium | Establish clear SLAs with vendor in contract. Identify escalation paths before go-live |

5.  Success Metrics

5.1 How to Measure Migration Success

Migration success should be measured across three dimensions: technical performance, business process efficiency, and user adoption. Define these metrics before go-live so there is an objective basis for evaluation.

| System Uptime | Target 99.5% or above in the first 90 days post go-live |
| --- | --- |
| Data Accuracy | Less than 0.5% data discrepancy rate verified through post-migration reconciliation |
| User Adoption Rate | 80% of users logging into the new system independently within 30 days of go-live |
| Process Cycle Time | Measurable reduction in time for key processes such as purchase order creation, payroll processing, or financial close |
| Support Ticket Volume | Declining trend in support tickets week on week during hyper care period |
| Cost Savings | Quantified reduction in infrastructure and maintenance costs versus pre-migration baseline within 12 months |

6.  Conclusion

Migrating from PeopleSoft to a cloud ERP platform is one of the most significant technology decisions a mid-size enterprise can make. Done well, it is a genuine business transformation that delivers lasting competitive advantage. Done poorly, it becomes a costly, disruptive project that erodes trust in technology leadership.

The framework presented in this document is grounded in the realities of enterprise ERP consulting, not theoretical best practices. The five-phase approach, the emphasis on data quality and change management, and the risk framework are all drawn from direct experience with enterprise-scale PeopleSoft implementations.

The most important takeaway is this: successful cloud ERP migration is 30% technology and 70% people and process. Organizations that invest in stakeholder alignment, data quality, and user adoption are far more likely to achieve their migration goals than those that treat it as a purely technical exercise.

About the Author Payal Devendra Jarviya is an MBA candidate at SKKU Graduate School of Business in Seoul, South Korea, specializing in AI and Business Analytics and Marketing Analytics. Prior to her MBA, Payal spent 4 years at NTT DATA North America within the PeopleSoft Oracle practice, progressing from Graduate Trainee to Information Technology Analyst. In that role she supported enterprise PeopleSoft implementations across operations and supply chain for global clients, resolving 20 to 30 system issues per release cycle and collaborating across 10-member cross-functional teams. This framework reflects her direct experience with PeopleSoft environments and enterprise change management in large-scale consulting engagements. LinkedIn: linkedin.com/in/payal-jarviya