WHITE PAPER

PeopleSoft to Cloud ERP

A Migration Framework for Mid-Size Enterprises

Payal Devendra Jarviya MBA Candidate ¦ SKKU Graduate School of Business, Seoul, South Korea Former IT Analyst ¦ NTT DATA North America ¦ PeopleSoft Oracle Practice (4 Years) linkedin.com/in/payal-jarviya ¦ 2025

| Topic ERP Migration & Cloud Strategy | Industry Enterprise Technology / Consulting | Audience IT Leaders, CFOs, Operations Directors |
| --- | --- | --- |

# Table of Contents

| Section | Page |
| --- | --- |
| Executive Summary | 3 |
| 1. The Case for Migration | 4 |
| 2. Pre-Migration Assessment | 5 |
| 3. The Migration Framework | 7 |
| 4. Cost-Benefit Analysis | 11 |
| 5. Real-World Case References | 13 |
| 6. Risk Management | 14 |
| 7. Success Metrics | 15 |
| 8. Conclusion | 16 |
| Glossary of ERP Terms | 17 |
| Appendix A: Readiness Assessment Template | 19 |
| Appendix B: Fit-Gap Analysis Template | 20 |
| Appendix C: UAT Sign-Off Template | 21 |

# Executive Summary

Many mid-size enterprises continue to rely on legacy PeopleSoft ERP systems implemented a decade or more ago. While these systems remain functional, they increasingly struggle to meet modern business demands: real-time analytics, remote accessibility, scalability, and AI integration.

This white paper provides a structured, practical framework for migrating from on-premises PeopleSoft to modern cloud ERP. It is designed specifically for mid-size enterprises with limited IT budgets, lean transformation teams, and complex stakeholder environments.

Drawing on four years of hands-on PeopleSoft consulting experience at NTT DATA North America, this framework addresses the full migration lifecycle from readiness assessment through to post-migration optimization.

Key Findings Global cloud ERP market projected to reach USD 40.5 billion by 2025, growing at 13.6% CAGR (Gartner, 2024). Mid-size enterprises migrating to cloud ERP report an average 25 to 30% reduction in IT infrastructure costs within 2 years. 70% of ERP migration failures are attributable to change management and people factors, not technical issues (McKinsey, 2023). Companies on on-premises PeopleSoft face average annual maintenance costs of USD 500K to USD 2M. Cloud ERP implementations deliver full ROI within 2.5 to 3 years on average for mid-size enterprises.

# 1.  The Case for Migration

## 1.1 Why PeopleSoft Enterprises Are at a Crossroads

| Pressure Factor | Detail |
| --- | --- |
| Vendor Direction | Oracle has shifted primary R&D to Oracle Cloud Fusion. PeopleSoft receives security patches but minimal new functionality. |
| Infrastructure Costs | On-premises PeopleSoft requires dedicated servers, DBA resources, and ongoing patches. Annual costs: USD 500K to USD 2M for mid-size firms. |
| Integration Complexity | Modern enterprises need seamless integration with CRM, BI, and AI tools. PeopleSoft integrations are largely custom-built and brittle. |
| Talent Scarcity | The pool of certified PeopleSoft consultants is shrinking. Cloud ERP skills are widely available. |
| Remote Accessibility | PeopleSoft was built for on-premises access. Post-pandemic hybrid work demands cloud-native, device-agnostic systems. |
| Reporting Limitations | PeopleSoft reporting requires SQL or PS Query knowledge. Cloud ERPs offer self-service dashboards out of the box. |

## 1.2 Market Growth

Cloud ERP Market Size (USD Billions)

2020; $22B.

2021; $26B.

2022; $30B.

2023; $35B.

2024; $38B.

2025 (Projected); $40.5B.

Source: Gartner Cloud ERP Market Guide, 2024

## 1.3 Expected Benefits Post-Migration

Benefits Reported After Cloud ERP Migration (% of companies)

Reduced IT infrastructure cost; 78%.

Improved reporting and analytics; 74%.

Faster deployment of new features; 71%.

Better cross-team collaboration; 65%.

Improved compliance and security; 63%.

Scalability without added infrastructure; 58%.

Source: Panorama Consulting ERP Report, 2023

# 2.  Pre-Migration Assessment

## 2.1 Organizational Readiness Framework

| Dimension | What to Assess |
| --- | --- |
| Process Documentation | Are current PeopleSoft business processes fully documented? Undocumented processes are a major migration risk. |
| Data Quality | What is the current state of master and transactional data? Duplicates, missing fields, and format issues must be resolved before migration. |
| Stakeholder Alignment | Do Finance, HR, Supply Chain, and IT leaders all support the migration? Misalignment at leadership level is the top cause of stalled projects. |
| IT Capability | Does the internal team have cloud skills? Identify gaps early and plan for upskilling or external support. |
| Budget Clarity | Is the full migration budget approved, including a 20% contingency buffer? |
| Change Management Plan | Who will own user adoption? Research shows technology is only 30% of ERP success. |

## 2.2 Common PeopleSoft Pain Points

- Heavily customized configurations that deviate from vanilla functionality, making cloud mapping complex

- Undocumented workarounds built around system limitations over years of operation

- Data inconsistencies between HR, Finance, and Supply Chain modules

- Shadow systems such as Excel trackers and Access databases filling PeopleSoft functionality gaps

- No data governance framework, resulting in duplicated or conflicting records

- Institutional knowledge existing only in the minds of long-tenured staff with no documentation

## 2.3 Migration Approach Options

| Approach | Timeline | Risk Profile | Best For |
| --- | --- | --- | --- |
| Big Bang | 6 to 12 months | HIGH: Full cutover at once. Any failure affects entire organization. | Smaller firms with simple processes and strong IT capability. |
| Phased | 12 to 24 months | MEDIUM: Migrate module by module. Issues contained to one area. RECOMMENDED. | Most mid-size enterprises. Best balance of risk and speed. |
| Parallel Run | 18 to 30 months | LOW: Run both systems simultaneously. Most expensive but safest. | Highly regulated industries with zero tolerance for downtime. |

# 3.  The Migration Framework

## 3.1 Five-Phase Overview

| Phase | Timeline | Key Activities | Primary Deliverable |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1 to 4 | Stakeholder interviews, current state mapping, business case, executive sign-off | Migration Readiness Report |
| Phase 2 | Weeks 5 to 10 | Vendor evaluation, fit-gap analysis, data quality audit, integration mapping | Vendor Selection Report + Data Quality Assessment |
| Phase 3 | Weeks 11 to 20 | System configuration, data cleansing, integration build, UAT preparation | Configured Cloud ERP + Clean Data Set |
| Phase 4 | Weeks 21 to 26 | UAT execution, defect resolution, user training, cutover planning | UAT Sign-off + Trained User Base |
| Phase 5 | Weeks 27 to 30 | Go-live, hyper care support, performance monitoring, post-migration review | Live System + Post-Migration Report |

## 3.2 Phase 1: Discovery and Business Case

Key Activities

- Conduct structured stakeholder interviews across Finance, HR, Supply Chain, and IT

- Document all active PeopleSoft modules, customizations, and integration points

- Quantify current annual infrastructure, licensing, and maintenance costs

- Develop 5-year ROI model comparing stay-the-course versus migration

- Present business case to C-suite and obtain formal project charter sign-off

Practitioner Insight Projects that skip or rush the discovery phase are 3 times more likely to experience scope changes and budget overruns mid-project. A strong business case does three things: quantifies the cost of inaction, sets realistic expectations, and establishes the metrics by which success will be measured post go-live. At NTT DATA, the most common failure point was not technical complexity but insufficient stakeholder alignment at the start of the project.

## 3.3 Phase 2: Vendor Selection and Fit-Gap Analysis

| Evaluation Criterion | What to Assess |
| --- | --- |
| Functional Coverage | Does the platform cover your core modules: HR, Finance, Procurement, Supply Chain? |
| PeopleSoft Migration Tools | Does the vendor offer PeopleSoft-specific data templates or migration accelerators? |
| Total Cost of Ownership | Compare license, implementation, and subscription costs over a 5-year horizon. |
| Integration Ecosystem | How easily does the platform connect with your existing CRM, BI, and third-party tools? |
| Regional Support | Does the vendor have certified implementation partners in your operating region? |
| AI and Analytics | What native AI and self-service reporting capabilities are included in the base license? |
| Upgrade Path | How are new features delivered? What is the vendor roadmap for the next 3 to 5 years? |

Fit-Gap Classifications

- FIT: Cloud ERP handles the process in standard configuration. No changes required.

- PARTIAL FIT: Cloud ERP handles the process with minor configuration or workflow adjustment.

- GAP: Cloud ERP does not support the process in standard configuration. Requires customization, workaround, or process redesign.

A gap rate above 30% of processes is a warning signal. Either the vendor is not the right fit, or the enterprise must redesign core processes before migration.

## 3.4 Phase 3: Build, Configure, and Data Migration

Data Migration Golden Rules

Five Rules That Prevent Migration Failures Rule 1: Never migrate dirty data. Cleanse first, migrate second. Rule 2: Test migration scripts with production-like data, not dummy data. Rule 3: Validate every migrated record against source PeopleSoft data before go-live sign-off. Rule 4: Keep PeopleSoft live as a read-only fallback until data validation is 100% complete. Rule 5: Assign one named person as data migration owner. Shared ownership means no ownership.

## 3.5 Phase 4: UAT and Training

| UAT Element | Standard |
| --- | --- |
| Test Scope | All in-scope business processes tested end-to-end, not just individual transactions |
| Test Data | Anonymized production data used wherever possible |
| Defect Classification | Critical (blocks go-live), Major (workaround available), Minor (cosmetic or low impact) |
| Pass Criteria | 100% of Critical defects resolved. 95% of Major defects resolved before sign-off. |
| Regression Testing | All previously passing cases re-executed after each batch of defect fixes |
| Business Sign-off | Named business owner from each function must formally sign UAT completion |

Training Strategy

- Role-based training: different content for end users, managers, approvers, and system administrators

- Deliver training within two weeks of go-live to maximize retention

- Create quick reference cards for the top 10 most common tasks in the new system

- Identify and certify super users in each department to provide first-line peer support post go-live

- Record all training sessions for future onboarding of new employees

## 3.6 Phase 5: Go-Live and Hypercare

Hypercare Protocol Weeks 1 to 2: War room activated. All critical issues resolved within 4 hours. Weeks 3 to 4: Daily issue triage. SLA extends to 8 hours for critical, 24 hours for major issues. Weeks 5 to 6: Weekly issue reviews. Super users take on first-line support. Weeks 7 to 8: Transition to BAU support. Formal hyper care closure review. Throughout: PeopleSoft remains live as read-only reference. Do not decommission until 12 weeks post go-live.

# 4.  Cost-Benefit Analysis

## 4.1 Typical Migration Cost Profile

The following estimates are based on industry benchmarks for mid-size enterprises with 500 to 2,000 users. Actual costs will vary based on scope, customization level, and vendor.

| Cost Category | Low Estimate | High Estimate | Notes |
| --- | --- | --- | --- |
| Cloud ERP Licenses (Year 1) | $150,000 | $400,000 | Per user pricing. Varies by vendor and scope. |
| Implementation and Consulting | $300,000 | $800,000 | Largest cost driver. Depends on customization level. |
| Data Cleansing and Migration | $50,000 | $150,000 | Frequently underestimated. Budget generously. |
| Training and Change Management | $40,000 | $100,000 | Critical investment. Do not reduce this budget. |
| Infrastructure Transition | $20,000 | $60,000 | Decommissioning on-premises servers. |
| Contingency (20%) | $112,000 | $302,000 | Industry standard. Strongly recommended. |
| TOTAL MIGRATION COST | $672,000 | $1,812,000 | One-time investment for full transformation. |

## 4.2 Annual Savings Post-Migration

Estimated Annual Savings Post-Migration (USD, Mid-Size Enterprise)

Server and infrastructure elimination; $280K/yr.

Reduced DBA and IT maintenance; $180K/yr.

Lower consulting and patch management; $120K/yr.

Productivity gains from improved UX; $95K/yr.

Reduced license upgrade costs; $80K/yr.

Total estimated annual savings: USD 755,000 per year post full migration.

## 4.3 ROI Timeline

| Metric | Year 0 | Year 1 | Year 2 | Year 3 | Year 4+ |
| --- | --- | --- | --- | --- | --- |
| Migration Cost | ($1.2M) | ($200K) | ($100K) | ($80K) | ($80K) |
| Annual Savings | $0 | $300K | $600K | $755K | $755K |
| Cumulative Net | ($1.2M) | ($1.1M) | ($600K) | $75K | $750K+ |
| ROI Status | Investment | Investment | Break-even approaching | POSITIVE ROI | Full ROI achieved |

Based on mid-range migration cost of USD 1.2M and average annual savings of USD 755K, full ROI is typically achieved in 2.5 to 3 years.

# 5.  Real-World Case References

## 5.1 Lessons from Large-Scale ERP Migrations

The following cases are drawn from publicly documented migrations. While these organizations are larger than a typical mid-size enterprise, the principles and failure modes are directly transferable.

Case 1: Unilever ¦ PeopleSoft to SAP Cloud Organization: Unilever (global FMCG, 190,000 employees across 190 countries) Migration: Fragmented legacy ERP including PeopleSoft HR to SAP S/4HANA Cloud Key Lessons: 1. Standardized business processes BEFORE migration rather than replicating local variations. Reduced customizations by 60%. 2. Dedicated 40% of total project budget to training and user adoption activities. 3. Chose a phased, region-by-region rollout over 4 years instead of a big bang approach. Outcome: 30% reduction in HR process costs. Real-time workforce analytics across all markets. Source: SAP Case Study Library, 2022

Case 2: City of Los Angeles ¦ PeopleSoft to Oracle Cloud Organization: City of Los Angeles, USA (public sector, 50,000 employees) Migration: PeopleSoft HR and Finance to Oracle Cloud HCM and ERP Key Lessons: 1. Data quality audit found 23% of employee records had incomplete or inconsistent data. Cleansing this before migration prevented significant post go-live issues. 2. Over 200 department-level Excel shadow systems were formally identified and retired as part of the project. 3. 180 super users were trained across 44 city departments, creating an internal adoption network. Outcome: USD 12M in annual operational savings. Employee self-service adoption of 87% within 6 months. Source: Oracle Customer Success Story, 2023

Case 3: Mid-Size Manufacturing Firm ¦ PeopleSoft 9.1 to Cloud ERP (Anonymized) Organization: Mid-size manufacturing firm, 800 employees, 3 sites across 2 countries Note: Details anonymized. Based on consulting engagement experience at NTT DATA. Key Lessons: 1. Of 47 PeopleSoft customizations in active use, only 12 were business-critical post fit-gap analysis. Retiring the remaining 35 simplified the migration significantly. 2. The project experienced a 6-week delay in Phase 3 due to data quality issues not fully scoped in Phase 1, reinforcing the importance of adequate discovery investment. 3. Parallel running PeopleSoft for 8 weeks post go-live proved critical when three integration failures were found in week 2. Outcome: 28% reduction in supply chain reporting time. Full ROI achieved in 2.7 years.

# 6.  Risk Management

## 6.1 Migration Risk Register

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Data loss or corruption during migration | High | Critical | Multiple data validation checkpoints. Maintain PeopleSoft as read-only backup for 12 weeks post go-live. |
| User resistance and low adoption | High | High | Invest in change management from Phase 1. Involve business users in design, not just testing. |
| Scope creep extending timeline and budget | High | High | Define scope boundaries in Phase 1. Use formal change request process for any additions. |
| Integration failures with connected systems | Medium | High | Map all integrations in Phase 1. Test in isolated environment before UAT begins. |
| Key person dependency | Medium | Medium | Document all decisions and configurations. Crosstrain team members throughout the project. |
| Budget overrun | Medium | High | Build 20% contingency into budget. Monthly budget tracking from Phase 1 onwards. |
| Vendor support limitations post go-live | Low | Medium | Negotiate SLAs in contract. Identify escalation paths before go-live date. |

# 7.  Success Metrics

## 7.1 KPI Framework

Define these metrics before go-live. Without pre-agreed success criteria, it is impossible to objectively evaluate whether the migration achieved its goals.

| KPI | Target Benchmark |
| --- | --- |
| System Uptime | 99.5% or above in first 90 days post go-live |
| Data Accuracy Rate | Less than 0.5% discrepancy rate in post-migration reconciliation |
| User Adoption Rate | 80% of users logging in independently within 30 days of go-live |
| Support Ticket Volume | Declining week-on-week trend during 8-week hyper care period |
| Process Cycle Time | Measurable reduction in purchase order creation, payroll run, and financial close |
| Training Completion | 100% of named users completing role-based training before go-live |
| Infrastructure Cost Reduction | Quantified reduction versus pre-migration baseline within 12 months |
| ROI Achievement | Positive cumulative ROI within 36 months of go-live |

# 8.  Conclusion

Migrating from PeopleSoft to a cloud ERP platform is one of the most significant technology decisions a mid-size enterprise will make. Done well, it delivers lasting competitive advantage through reduced costs, better data, and a technology foundation ready for AI-driven innovation.

This framework is grounded in the realities of enterprise ERP consulting, not theoretical best practices. The five-phase approach, the emphasis on data quality and change management, and the risk register all reflect direct experience with PeopleSoft environments at enterprise scale.

The most important insight: successful cloud ERP migration is 30% technology and 70% people and process. Organizations that invest in stakeholder alignment, data quality, and user adoption consistently outperform those that treat migration as a purely technical exercise.

About the Author Payal Devendra Jarviya is an MBA candidate at SKKU Graduate School of Business in Seoul, South Korea, specializing in AI and Business Analytics and Marketing Analytics. Prior to her MBA, she spent 4 years at NTT DATA North America within the PeopleSoft Oracle practice, progressing from Graduate Trainee to Information Technology Analyst. She supported enterprise PeopleSoft implementations across operations and supply chain, resolving 20 to 30 system issues per release cycle and collaborating across 10-member cross-functional teams. Certifications: Oracle Cloud Infrastructure Foundations, Oracle Cloud Data Management, AI for Managers (Microsoft and LinkedIn), Business Analysis and Process Management (Coursera) LinkedIn: linkedin.com/in/payal-jarviya ¦ Email: payaljarviya@skku.edu

# Glossary of ERP Terms

| Term | Definition |
| --- | --- |
| BAU (Business as Usual) | Normal day-to-day business operations, as distinct from project or transformation activities. |
| Big Bang Migration | A migration approach where all users and processes switch to the new system simultaneously on a single go-live date. |
| Change Management | The structured process of managing the people side of change to achieve the desired business outcome from a new system. |
| Cloud ERP | Enterprise Resource Planning software hosted on remote servers, accessed via the internet, and managed by the vendor rather than the organization’s internal IT team. |
| Cutover | The point at which users stop using the old system and begin using the new system. The most operationally risky moment in any migration. |
| Data Cleansing | The process of detecting and correcting inaccurate, incomplete, duplicate, or improperly formatted records before migration. |
| ERP (Enterprise Resource Planning) | Integrated software that manages core business processes including Finance, HR, Supply Chain, and Operations in a single system. |
| Fit-Gap Analysis | A structured comparison between an organization’s required business processes and the standard functionality of a target cloud platform. |
| Go-Live | The date on which the new system becomes the operational system of record for the organization. |
| Hypercare | The intensive support period immediately following go-live, typically 4 to 8 weeks, with dedicated resources to resolve issues rapidly. |
| Legacy System | An older technology system still in use despite newer alternatives, often because replacing it is costly or complex. |
| Master Data | Core business data such as employee records, vendor lists, and customer accounts shared across multiple processes and systems. |
| Parallel Run | Running the old and new systems simultaneously after go-live to validate outputs and provide a fallback option. |
| PeopleSoft | An ERP suite originally developed by PeopleSoft Inc., acquired by Oracle in 2005. Widely used for HR, Finance, and Supply Chain. |
| Phased Migration | A migration approach where different modules or business units migrate sequentially in waves rather than all at once. |
| ROI (Return on Investment) | A financial metric measuring net benefit relative to cost. Expressed as a percentage or payback period in years. |
| SaaS (Software as a Service) | A software delivery model where applications are hosted in the cloud and accessed via subscription, not installed locally. |
| Shadow System | An unofficial system such as an Excel spreadsheet used alongside the official ERP to fill functionality gaps. |
| Super User | A business user who receives advanced system training and serves as a first point of contact for peer support post go-live. |
| UAT (User Acceptance Testing) | The final testing phase in which business users validate that the configured system meets requirements before go-live sign-off. |

# Appendix A: Organizational Readiness Assessment Template

Score each dimension from 1 (not ready) to 5 (fully ready). A total score below 18 indicates the organization needs significant preparation before beginning migration.

| Dimension | Assessment Questions | Score (1-5) | Actions Required |
| --- | --- | --- | --- |
| Process Documentation | Are current-state processes documented? Are process owners identified? | __ / 5 |  |
| Data Quality | Has a data quality assessment been done? Are data owners assigned? | __ / 5 |  |
| Stakeholder Alignment | Do all executive sponsors formally support the migration? | __ / 5 |  |
| IT Capability | Does the IT team have cloud skills? Have gaps been resourced? | __ / 5 |  |
| Budget Clarity | Is the full migration budget approved including 20% contingency? | __ / 5 |  |
| Change Management | Is a change lead assigned? Is a communication plan in place? | __ / 5 |  |
| TOTAL SCORE | 18 to 30: Proceed. 12 to 17: Address gaps first. Below 12: Not ready. | __ / 30 |  |

# Appendix B: Fit-Gap Analysis Template

Complete one row per business process during Phase 2. The output directly informs implementation scope, timeline, and budget.

| Process Area | Process Name | Classification | Priority | Action Required |
| --- | --- | --- | --- | --- |
| HR | Employee Onboarding | FIT | High | No action required. Standard cloud ERP workflow covers this. |
| HR | Performance Review | PARTIAL FIT | Medium | Minor config needed to match existing rating scale and workflow. |
| Finance | Purchase Order Approval | GAP | High | Custom approval matrix required. Estimated 3 days development. |
| Finance | Multi-Currency Payments | FIT | High | Standard functionality. No customization needed. |
| Supply Chain | Vendor Portal Integration | GAP | Medium | API integration with existing vendor portal required. |
| [Area] | [Process Name] | [FIT / PARTIAL / GAP] | [H/M/L] | [Describe required action] |

# Appendix C: UAT Sign-Off Template

Use this template at the end of Phase 4 to formally record UAT completion and obtain business sign-off before go-live is authorized.

| Field | Details |
| --- | --- |
| Project Name | PeopleSoft to Cloud ERP Migration |
| Organization | [Organization Name] |
| UAT Period | [Start Date] to [End Date] |
| Total Test Cases Executed | [Number] |
| Critical Defects Found | [Number] |
| Critical Defects Resolved | [Number] |
| Major Defects Found | [Number] |
| Major Defects Resolved | [Number] |
| Minor Defects Outstanding | [Number] (acceptable for go-live with agreed resolution plan) |
| UAT Pass Criteria Met | Yes / No |
| Go-Live Recommendation | APPROVED TO PROCEED / NOT APPROVED |

| Function | Authorized Signature and Date |
| --- | --- |
| Finance Lead | ________________________________ |
| HR Lead | ________________________________ |
| Supply Chain Lead | ________________________________ |
| IT Lead | ________________________________ |
| Executive Sponsor | ________________________________ |

By signing above, business representatives confirm UAT has been completed to the agreed standard, and the system is approved for go-live.